## Sprint Board
Column | Tag | Task | Description | Reference
To Do | Increment 2 | Observation Drafting sub-workflow | Row-by-row over the completed audit working file: draft criteria/condition/cause/risk/recommendation, assign rating from residual risk level, flag insufficient-evidence causes instead of inventing (GR-04). | Referenced by orchestrator, not yet built
To Do | Increment 2 | Parser: completed audit working file (xlsx) | Row extraction into working_file_row — risk, control, test steps, work done, test status/result, residual risk level, evidence refs.
To Do | Increment 2 | Parser: kick-off deck (pptx) | Objectives, scope, review period, stakeholder/acknowledgment text, 3 audit-team name+title pairs (D-3).
To Do | Increment 2 | Parser: optional inputs incl. legacy .ppt | Audit notification, process understanding (must read legacy binary .ppt per FR-05), analysis sheet.
To Do | Increment 3 | Round-trip Reconciliation sub-workflow | Diff an auditor-edited, re-uploaded Word file against stable paragraph ids; map changes back to observation rows; update state store as new source of truth (FR-21).
To Do | Increment 3 | Final Issue sub-workflow | Check all observations approved/frozen, flip status Draft to Final, emit Word + PDF + Summary Observations PPTX, close chat.
To Do | Increment 3 | Summary Observations PPTX renderer | One-to-two-slide render into Beyon's existing template: title/logo, key observations one line each, brief action plan + status.
To Do | Increment 4 | Template fidelity validator (GR-02) | Automated structural diff of generated Word doc vs fixed template - section order, table shapes, rating labels/colours - before it reaches the reviewer.
To Do | Increment 4 | End-to-end test on the CVM pilot dataset | Full run against the real RCM_CVM_Review + kick-off deck + issued report as ground truth, scored against Beyon's 10-point + 8-point acceptance criteria.
In Progress |  | Nothing active right now | Pick up from To Do for the next increment.
Review | Increment 1 | Build v0.1 package | State-store schema + orchestrator + Intake & Parse + Front-Matter Assembly + Document Assembly + Refinement, delivered as build_v0.1.zip. Awaiting review before Increment 2 starts.
Done | Increment 1 | Postgres state-store schema | engagement, source_document, working_file_row, observation, appendix_item, change_log. Frozen-observation trigger enforces GR-01 at the data layer. | sql/001_schema.sql
Done | Increment 1 | Orchestrator workflow | Form Trigger -> new engagement path; Chat Trigger -> resolve session to existing engagement only (no new-engagement path via chat). | workflows/01_orchestrator.json
Done | Increment 1 | Intake & Parse sub-workflow | Classifies uploads, validates mandatory inputs, records gaps for optional ones (FR-23), fans out to per-file-type parsers. | workflows/02_intake_and_parse.json
Done | Increment 1 | Front-Matter Assembly sub-workflow | Verbatim + fill + opinion-lookup + generated-background sections, grounded per GR-03/GR-04. | workflows/03_front_matter_assembly.json
Done | Increment 1 | Document Assembly sub-workflow | Deterministic render from state store, rebuilds TOC/List of Issues/Dashboard, tags stable paragraph ids for round-trip mapping. | workflows/04_document_assembly.json
Done | Increment 1 | Refinement sub-workflow (chat) | Scoped to Detailed Audit Issues. 8 instruction types, narrow context per edit, GR-01 frozen-block, change-log on every mutation. | workflows/05_refinement.json
Done | Increment 1 | Overall opinion paragraph library | Transcribed from the BRD image, cross-checked against the issued CVM report. Marked provisional pending D-2. | overall_opinion_library.json
Done | Increment 1 | HLD + end-to-end flowchart | Architecture doc and visual flow covering intake, refinement loop, round-trip, and final issue. | HLD_Internal_Audit_Report_Drafter.md
Blocked | Beyon dependency | Confirm overall opinion library (D-2) | Our provisional transcription needs sign-off against Beyon's live SOP text before it's treated as final.
Blocked | Beyon dependency | Appendix selection rule beyond length heuristic (D-4) | Needed to finalize the auto-direction logic in appendix_item / Document Assembly.
Blocked | Beyon dependency | Area for Improvement issue type (FR-26 origin) | Seen in the issued CVM report but not in the written requirements sheet - needs confirmation in Beyon's review markup.
Blocked | Beyon dependency | Effort baseline for time-saving metric (D-5) | No manual baseline agreed yet; needed before the O-1 time-saving criterion can be measured rather than reported as indicative.
Blocked | Beyon dependency | Process-understanding embedded images - scope decision | Ignore / carry as appendix reference only / agent-placed - needs a decision before Observation Drafting or Front-Matter Assembly touch this.
Blocked | Beyon dependency | 2-3 additional worked engagements (D-1) | Needed so pilot acceptance isn't judged on the CVM engagement alone.
Blocked | Beyon dependency | Named reviewers & availability across 6 weeks (D-6) | Needed to schedule the human-review scoring pass in Section 11.2.

## Summary
Column | Task Count
To Do | 9
In Progress | 1
Review | 1
Done | 8
Blocked | 7